## README
RedLine Medical — Project Team and Roles
Project | RedLine Medical Supplies & Equipment Trading — Odoo ERP Graduation Project
Project window (simulated) | 2026-10-01 to 2026-10-20
Business reporting period | 1 May 2026 – 30 September 2026
Document date | 2026-10-25
Status basis | All 38 documentation/design/data-preparation tasks are shown at 100% as the project register for this graduation simulation. 100% means the documented deliverable exists; it does NOT mean the solution has been installed or tested on a live Odoo server.
Formulas | Summary sheet figures are computed with COUNTIFS/AVERAGEIFS from the Task List.
Sheets | Team Register · Roles and Responsibilities · Task List · Deliverable Register · Milestones · Summary (variant B adds Module Responsibility Matrix)

## Team Register
Member ID | Name | Role | Primary Responsibilities | Team | Note
TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | App installation, general settings, companies and branches; Users, access rights, record rules and approval workflows (permissions); Solution design, GAWF, SSD and final integration of all documents; Project governance, presentation and final review | Core project team | Simulated project member
TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | Sales and CRM configuration: pipeline, quotations, pricelists, sales teams; Customer master data and contract pricing (preparing and uploading files); BRD, RTM and business process documentation; Sales and CRM test scenarios and business acceptance | Core project team | Simulated project member
TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | Inventory configuration: warehouses, locations, routes, lots, serials, expiry, FEFO; Product master, opening stock and reordering rules; Data upload: preparing and importing all CSV files and data quality checks; Technical proposal, go-live plan and package validation | Core project team | Simulated project member
TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | Purchase configuration: vendors, RFQ and PO, approvals, vendor pricelists; Quality inspection, receipts follow-up and supplier returns; UAT execution, defect log and test documentation; User's guide, training and final quality assurance | Core project team | Simulated project member
TM-05 | Omnia Haitham | Accounting & Finance | Accounting configuration: chart of accounts, journals, taxes, payment terms; Invoices, bills, payments, credit notes, bank and cash; Opening balances, stock valuation and financial reconciliations; Financial proposal (FPD) and accounting test scenarios | Core project team | Simulated project member

## Roles and Responsibilities
Member ID | Name | Role | Resp. ID | Responsibility | RACI
TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | R1 | App installation, general settings, companies and branches | Accountable owner
TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | R2 | Users, access rights, record rules and approval workflows (permissions) | Accountable owner
TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | R3 | Solution design, GAWF, SSD and final integration of all documents | Accountable owner
TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | R4 | Project governance, presentation and final review | Accountable owner
TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | R1 | Sales and CRM configuration: pipeline, quotations, pricelists, sales teams | Accountable owner
TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | R2 | Customer master data and contract pricing (preparing and uploading files) | Accountable owner
TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | R3 | BRD, RTM and business process documentation | Accountable owner
TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | R4 | Sales and CRM test scenarios and business acceptance | Accountable owner
TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | R1 | Inventory configuration: warehouses, locations, routes, lots, serials, expiry, FEFO | Accountable owner
TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | R2 | Product master, opening stock and reordering rules | Accountable owner
TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | R3 | Data upload: preparing and importing all CSV files and data quality checks | Accountable owner
TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | R4 | Technical proposal, go-live plan and package validation | Accountable owner
TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | R1 | Purchase configuration: vendors, RFQ and PO, approvals, vendor pricelists | Accountable owner
TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | R2 | Quality inspection, receipts follow-up and supplier returns | Accountable owner
TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | R3 | UAT execution, defect log and test documentation | Accountable owner
TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | R4 | User's guide, training and final quality assurance | Accountable owner
TM-05 | Omnia Haitham | Accounting & Finance | R1 | Accounting configuration: chart of accounts, journals, taxes, payment terms | Accountable owner
TM-05 | Omnia Haitham | Accounting & Finance | R2 | Invoices, bills, payments, credit notes, bank and cash | Accountable owner
TM-05 | Omnia Haitham | Accounting & Finance | R3 | Opening balances, stock valuation and financial reconciliations | Accountable owner
TM-05 | Omnia Haitham | Accounting & Finance | R4 | Financial proposal (FPD) and accounting test scenarios | Accountable owner

## Task List
Task ID | Phase | Task | Description | Owner | Start Date | End Date | Priority | Deliverable | Dependencies | Status | Progress % | Acceptance Criteria
T-001 | 1 Initiation | Project kick-off and charter | Define scope, objectives, governance, branch/warehouse structure and success criteria. | Mohamed Mahmoud Abdel Bary | 2026-10-01 | 2026-10-01 | High | Project charter (in SSD §1) |  | Completed | 100% | Charter approved by the team leader
T-002 | 1 Initiation | Company profile and business context | Compile bilingual company profile, branches, warehouse network, product categories and customers. | Mohamed Essam El-Din Youssef | 2026-10-01 | 2026-10-04 | High | Company_Profile.docx | T-001 | Completed | 100% | Profile reviewed; facts consistent with the charter
T-003 | 1 Initiation | Project team, roles and task register | Define five-member team, responsibilities, task register and milestones. | Mohamed Mahmoud Abdel Bary | 2026-10-01 | 2026-10-01 | High | Project_Team_and_Roles.xlsx | T-001 | Completed | 100% | Every deliverable has an accountable owner
T-004 | 1 Initiation | Odoo version and edition assumptions | Select version/edition, list standard vs Enterprise vs custom features. | Mohamed Mahmoud Abdel Bary | 2026-10-01 | 2026-10-01 | High | Assumptions (BDC §1, TPD §2) | T-001 | Completed | 100% | Version stated; unverified features flagged
T-005 | 2 Analysis | Stakeholder analysis and interviews (simulated) | Identify stakeholders, document as-is processes of the legacy/manual baseline. | Mohamed Essam El-Din Youssef | 2026-10-04 | 2026-10-05 | High | BRD §3-4 | T-002 | Completed | 100% | Stakeholder register approved
T-006 | 2 Analysis | As-is process documentation | Document manual quotation, purchasing, receiving, stock-card, invoicing and collection processes. | Mohamed Essam El-Din Youssef | 2026-10-05 | 2026-10-06 | High | BRD §4; GAWF §3 | T-005 | Completed | 100% | Processes validated with owners
T-007 | 2 Analysis | Functional and non-functional requirements | Write requirements with IDs, priorities, owners and acceptance criteria. | Mohamed Essam El-Din Youssef | 2026-10-06 | 2026-10-07 | High | BRD §6-8 | T-006 | Completed | 100% | All requirements baselined
T-008 | 2 Analysis | Business rules, roles and reporting requirements | Capture rules for credit, FEFO, quarantine, approvals; define reports and KPIs. | Mohamed Essam El-Din Youssef | 2026-10-07 | 2026-10-08 | High | BRD §9-11 | T-007 | Completed | 100% | Rules reviewed
T-009 | 2 Analysis | Gap analysis and workflow documentation (GAWF) | Compare manual baseline with proposed Odoo processes; propose solutions per gap. | Mohamed Mahmoud Abdel Bary | 2026-10-07 | 2026-10-08 | High | GAWF_Gap_Analysis.docx | T-006, T-007 | Completed | 100% | Each gap has solution, owner, priority, validation
T-010 | 2 Analysis | Requirements traceability matrix | Map each requirement to process, module, feature class, owner and test case. | Mohamed Essam El-Din Youssef | 2026-10-07 | 2026-10-08 | High | RTM_Traceability_Matrix.xlsx | T-007 | Completed | 100% | Every requirement linked to a test case
T-011 | 3 Design | Solution architecture and module selection | Define modules, dependencies, single-company/multi-branch model, warehouse routes. | Mohamed Mahmoud Abdel Bary | 2026-10-07 | 2026-10-08 | High | SSD §2-4 | T-007 | Completed | 100% | Architecture approved
T-012 | 3 Design | Security model and approval workflows | Define roles, groups, record-rule limitations, approval thresholds and audit trail. | Mohamed Mahmoud Abdel Bary | 2026-10-08 | 2026-10-11 | High | SSD §7 | T-011 | Completed | 100% | Segregation of duties documented
T-013 | 3 Design | Process diagrams (P2P, O2C, receipt, transfers, returns, close) | Create workflow diagrams for six core processes. | Mohamed Mahmoud Abdel Bary | 2026-10-08 | 2026-10-11 | High | SSD §8 | T-011 | Completed | 100% | Diagrams consistent with requirements
T-014 | 3 Design | Solution Design Document (SSD) | Assemble SSD with reporting design and migration strategy. | Mohamed Mahmoud Abdel Bary | 2026-10-11 | 2026-10-12 | High | SSD_Solution_Design.docx | T-011, T-012, T-013 | Completed | 100% | SSD complete and reviewed
T-015 | 3 Design | Technical proposal (TPD) | Define technical scope, integration, custom module proposals, testing, deployment, maintenance. | Ahmed Mahmoud Mohamed | 2026-10-08 | 2026-10-12 | High | TPD_Technical_Proposal.docx | T-011 | Completed | 100% | Custom work clearly labelled as proposed
T-016 | 3 Design | Financial proposal (FPD) | Prepare illustrative EGP estimate with milestones, exclusions and VAT assumption. | Omnia Haitham | 2026-10-12 | 2026-10-13 | Medium | FPD_Financial_Proposal.pdf | T-015 | Completed | 100% | Totals verified arithmetically
T-017 | 4 Data | Organization, branches and warehouses setup design | Design branch representation and four-warehouse structure with locations and routes. | Ahmed Mahmoud Mohamed | 2026-10-08 | 2026-10-11 | High | Organization_and_Accounting_Charts.xlsx (sheets 1-3) | T-004, T-011 | Completed | 100% | Branches/warehouses consistent in all documents
T-018 | 4 Data | Chart of accounts and journals design | Design 101-account hierarchical chart, journals, bank/cash accounts. | Omnia Haitham | 2026-10-11 | 2026-10-12 | High | Organization_and_Accounting_Charts.xlsx (sheets 4-5) | T-017 | Completed | 100% | No duplicate codes; account types valid
T-019 | 4 Data | Accounting configuration, tax and account mapping | Define valuation, Anglo-Saxon, VAT 14% assumption and category-to-account mapping. | Omnia Haitham | 2026-10-12 | 2026-10-13 | High | Organization_and_Accounting_Charts.xlsx (sheets 6-9) | T-018 | Completed | 100% | Mapping reconciles with simulated journal entries
T-020 | 4 Data | Product master, categories and tracking | Define 24 products with bilingual names, costs, tracking and expiry policies. | Ahmed Mahmoud Mohamed | 2026-10-11 | 2026-10-12 | High | Products_and_Inventory_Data.xlsx (sheets 1-2) | T-017 | Completed | 100% | Serial for equipment, lot+expiry for consumables
T-021 | 4 Data | Opening balances and reordering rules | Prepare warehouse opening stock and min/max rules. | Ahmed Mahmoud Mohamed | 2026-10-12 | 2026-10-13 | High | Products_and_Inventory_Data.xlsx (sheets 3,8) | T-020 | Completed | 100% | Opening value reconciles to opening journal
T-022 | 4 Data | Five-month stock movements, lots and serials | Generate coherent stock history with lot/serial registers and expiry tracking. | Ahmed Mahmoud Mohamed | 2026-10-13 | 2026-10-14 | High | Products_and_Inventory_Data.xlsx (sheets 4-7,9-10) | T-021 | Completed | 100% | Opening+in-out=closing for every product/warehouse
T-023 | 4 Data | Customer and vendor master data | Prepare 13 customers and 6 vendors (illustrative) with terms and credit limits. | Mohamed Essam El-Din Youssef | 2026-10-11 | 2026-10-12 | High | Partners_and_Operations_Cycles.xlsx (sheets 1-2) | T-017 | Completed | 100% | Partners flagged as illustrative
T-024 | 4 Data | Five-month sales and purchase cycles | Generate SOs, POs, deliveries, receipts, invoices, bills, payments and returns. | Ahmed Mahmoud Mohamed | 2026-10-14 | 2026-10-15 | High | Partners_and_Operations_Cycles.xlsx (sheets 3-10) | T-022, T-023 | Completed | 100% | Documents reconcile with stock and GL
T-025 | 4 Data | Monthly summaries and transaction reconciliation | Summaries, receivable/payable roll-forward and ledger cross-checks. | Omnia Haitham | 2026-10-15 | 2026-10-18 | High | Partners_and_Operations_Cycles.xlsx (sheets 11-12) | T-024 | Completed | 100% | All checks pass or are explained
T-026 | 4 Data | Data migration design and CSV import package | Define import order, dependencies, CSV files and README with limitations. | Ahmed Mahmoud Mohamed | 2026-10-15 | 2026-10-18 | High | Import_Package/ (CSV + README) | T-019, T-021, T-022, T-024 | Completed | 100% | Import order documented
T-027 | 4 Data | Data quality checks | Automated checks of keys, duplicates, dates and reconciliation. | Ahmed Mahmoud Mohamed | 2026-10-18 | 2026-10-19 | High | Validation_Report | T-025, T-026 | Completed | 100% | Zero structural errors
T-028 | 2 Analysis | Functional requirements validation | Validate requirements against design and data; resolve conflicts. | Mohamed Essam El-Din Youssef | 2026-10-12 | 2026-10-13 | High | Validation notes (RTM) | T-010, T-014 | Completed | 100% | No unresolved conflicts
T-029 | 5 QA & Training | UAT scenario and test-case documentation | Write test cases covering the full lifecycle with simulated data references. | Fathy Adel Fathy | 2026-10-08 | 2026-10-12 | High | UATD_User_Acceptance_Testing.xlsx | T-007, T-010 | Completed | 100% | Every requirement has a test case
T-030 | 5 QA & Training | Simulated UAT review | Review expected behaviour of each test against the documented scenario; record status honestly. | Fathy Adel Fathy | 2026-10-12 | 2026-10-13 | High | UATD results (simulated) | T-029 | Completed | 100% | Results labelled simulated; unverified items not marked passed
T-031 | 5 QA & Training | User guides | Prepare role-based guides (sales, purchase, warehouse, quality, accounting). | Fathy Adel Fathy | 2026-10-12 | 2026-10-14 | Medium | UDP_Users_Guide.docx | T-014 | Completed | 100% | Guides cover core tasks
T-032 | 5 QA & Training | Training materials and plan | Prepare training outline, exercises and assessment tasks. | Fathy Adel Fathy | 2026-10-14 | 2026-10-15 | Medium | TD_Training_Document.docx | T-031 | Completed | 100% | Plan approved
T-033 | 5 QA & Training | Basic database configuration document | Document initial Odoo setup: company, users, groups, settings, taxes, backups. | Mohamed Mahmoud Abdel Bary | 2026-10-12 | 2026-10-13 | High | Basic_Database_Configuration.docx | T-011, T-018 | Completed | 100% | No real credentials included
T-034 | 5 QA & Training | Business process and cycle documentation | Document the end-to-end cycles with examples from simulated records. | Mohamed Essam El-Din Youssef | 2026-10-15 | 2026-10-18 | Medium | BRD §5; SSD §8 | T-013, T-024 | Completed | 100% | Cycles tie to simulated data
T-035 | 1 Initiation | Project name and scope document | Define project identity, objectives, in/out of scope, deliverables, assumptions and acceptance criteria. | Mohamed Essam El-Din Youssef | 2026-10-05 | 2026-10-06 | High | Project_Name_and_Scope.docx | T-001, T-005 | Completed | 100% | Scope approved by the team leader
T-036 | 2 Analysis | CRM requirements and pipeline design | Define leads, opportunity stages, sales teams per branch, lost reasons and tender tracking; link won opportunities to sales orders. | Mohamed Essam El-Din Youssef | 2026-10-06 | 2026-10-07 | High | BRD §6.3 (CRM); SSD CRM design; GAWF G-28, G-29 | T-005, T-006 | Completed | 100% | CRM requirements CRM-001..CRM-008 baselined
T-037 | 3 Design | Users privileges document (UPD) | Define roles, groups, access matrix, approval limits and segregation of duties. | Mohamed Mahmoud Abdel Bary | 2026-10-13 | 2026-10-14 | High | UPD_Users_Privileges.docx | T-012, T-019 | Completed | 100% | Segregation of duties documented; no credentials
T-038 | 3 Design | Module configuration specifications (Sales/CRM, Purchase, Inventory, Accounting, general settings) | Specify app settings, journals, imports and access rights per Odoo area with the owner of each area. | Mohamed Mahmoud Abdel Bary | 2026-10-11 | 2026-10-12 | High | Basic_Database_Configuration.docx §7-10; Runbook | T-011, T-017 | Completed | 100% | Each Odoo area has an owner and a configuration checklist
T-039 | 4 Data | CRM pipeline sample data and CSV | Prepare simulated leads/opportunities linked to sales orders, stages and teams; add CSV 16 and reconciliation checks. | Mohamed Essam El-Din Youssef | 2026-10-15 | 2026-10-18 | Medium | Partners_and_Operations_Cycles.xlsx (CRM Pipeline); Import_Package/16_crm_pipeline.csv | T-022, T-024 | Completed | 100% | Won opportunities reconcile with non-retail sales orders
T-040 | 5 QA & Training | Go-live and deployment plan | Define readiness criteria, cut-over, reconciliation, rollback and hypercare. | Ahmed Mahmoud Mohamed | 2026-10-18 | 2026-10-19 | High | Go_Live_and_Deployment_Plan.docx | T-015, T-026 | Completed | 100% | Cut-over and rollback steps documented
T-041 | 4 Data | Accounting procedures and month-end close checklist | Document accounting procedures, reconciliation steps and month-end close for Odoo. | Omnia Haitham | 2026-10-18 | 2026-10-19 | Medium | Month-end close checklist (SSD / UDP section 7) | T-019, T-025 | Completed | 100% | Checklist matches simulated reconciliations
T-042 | 6 Closure | Presentation for graduation defense | Build 15-20 slide-style PDF. | Mohamed Mahmoud Abdel Bary | 2026-10-13 | 2026-10-14 | High | PowerPoint_Presentation.pdf | T-014, T-016, T-028 | Completed | 100% | Facts consistent with documents
T-043 | 6 Closure | Final quality assurance | Cross-document consistency check; fix defects. | Fathy Adel Fathy | 2026-10-19 | 2026-10-20 | High | Final QA notes | T-027, T-030, T-032, T-033, T-034, T-042, T-035, T-036, T-037, T-038, T-039, T-040, T-041 | Completed | 100% | No inconsistencies
T-044 | 6 Closure | Final review and project coordination | Final governance sign-off and package approval. | Mohamed Mahmoud Abdel Bary | 2026-10-20 | 2026-10-20 | High | Approval record | T-043 | Completed | 100% | Approved by team leader
T-045 | 6 Closure | ZIP packaging and validation report | Package deliverables and run automated validation. | Ahmed Mahmoud Mohamed | 2026-10-20 | 2026-10-20 | High | RedLine_Odoo_Graduation_Project.zip; Validation_Report | T-044 | Completed | 100% | All required files present and opening

## Deliverable Register
Deliverable ID | Deliverable | Package Path | Format | Accountable Owner | Status | Linked Tasks
D-001 | Project presentation (18 slides, editable) | 1. Project Presentation/PowerPoint_Presentation.pptx | PPTX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-042
D-002 | Project presentation (18 slides, PDF) | 1. Project Presentation/PDF_Presentations.pdf | PDF | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-042
D-003 | Project name and scope | 2. Project Preparations Documents/Project_Name_and_Scope.docx | DOCX | Mohamed Essam El-Din Youssef | Delivered (generated) | T-002, T-035
D-004 | Company profile (bilingual) | 2. Project Preparations Documents/Company_Profile.docx | DOCX | Mohamed Essam El-Din Youssef | Delivered (generated) | T-002
D-005 | Project team, roles and task register | 2. Project Preparations Documents/Project_Team_and_Roles.xlsx | XLSX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-003
D-006 | Basic database configuration | 2. Project Preparations Documents/Basic_Database_Configuration.docx | DOCX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-033, T-004
D-007 | Business requirements document (BRD) | 3. Project Documents/BRD_Business_Requirements.docx | DOCX | Mohamed Essam El-Din Youssef | Delivered (generated) | T-005 - T-008
D-008 | Requirements traceability matrix (RTM) | 3. Project Documents/RTM_Traceability_Matrix.xlsx | XLSX | Mohamed Essam El-Din Youssef | Delivered (generated) | T-010, T-028
D-009 | Solution design document (SSD) | 3. Project Documents/SSD_Solution_Design.docx | DOCX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-011 - T-014
D-010 | Gap analysis and workflow documentation (GAWF) | 3. Project Documents/GAWF_Gap_Analysis.docx | DOCX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-009
D-011 | Technical proposal (TPD) | 3. Project Documents/TPD_Technical_Proposal.docx | DOCX | Ahmed Mahmoud Mohamed | Delivered (generated) | T-015
D-012 | Users privileges document (UPD) | 3. Project Documents/UPD_Users_Privileges.docx | DOCX | Mohamed Mahmoud Abdel Bary | Delivered (generated) | T-037
D-013 | Training document (TD) | 3. Project Documents/TD_Training_Document.docx | DOCX | Fathy Adel Fathy | Delivered (generated) | T-032
D-014 | User's guide (UDP) | 3. Project Documents/UDP_Users_Guide.docx | DOCX | Fathy Adel Fathy | Delivered (generated) | T-031
D-015 | Financial proposal (FPD) | 3. Project Documents/FPD_Financial_Proposal.pdf | PDF | Omnia Haitham | Delivered (generated) | T-016
D-016 | User acceptance testing workbook (UATD) | 3. Project Documents/UATD_User_Acceptance_Testing.xlsx | XLSX | Fathy Adel Fathy | Delivered (generated) | T-029, T-030
D-017 | Organization and accounting charts | 4. Entity Data & Implementation Setup/Organization_and_Accounting_Charts.xlsx | XLSX | Omnia Haitham | Delivered (generated) | T-017 - T-019
D-018 | Products and inventory data | 4. Entity Data & Implementation Setup/Products_and_Inventory_Data.xlsx | XLSX | Ahmed Mahmoud Mohamed | Delivered (generated) | T-020 - T-022
D-019 | Go-live and deployment plan | 4. Entity Data & Implementation Setup/Go_Live_and_Deployment_Plan.docx | DOCX | Ahmed Mahmoud Mohamed | Delivered (generated) | T-040
D-020 | Partners and operations cycles | 4. Entity Data & Implementation Setup/Partners_and_Operations_Cycles.xlsx | XLSX | Ahmed Mahmoud Mohamed | Delivered (generated) | T-023 - T-025
D-021 | CSV import package and README (16 files) | 4. Entity Data & Implementation Setup/Import_Package/ | CSV + MD | Ahmed Mahmoud Mohamed | Delivered (generated) | T-026
D-022 | Validation report | 3. Project Documents/Supporting/Validation_Report.md | MD | Ahmed Mahmoud Mohamed | Delivered (generated) | T-027, T-043
D-023 | User guide and training outline (SSD appendix, BDC section 10) | 3. Project Documents/SSD_Solution_Design.docx | DOCX (sections) | Fathy Adel Fathy | Delivered (generated) | T-031, T-032

## Milestones
Milestone ID | Milestone | Target Date | Owner | Linked Tasks | Status
M-01 | Project kick-off and charter approved | 2026-10-01 | Mohamed Mahmoud Abdel Bary | T-001 | Achieved
M-02 | Requirements baseline (BRD + RTM) | 2026-10-08 | Mohamed Essam El-Din Youssef | T-007, T-010 | Achieved
M-03 | Solution design and GAWF approved | 2026-10-12 | Mohamed Mahmoud Abdel Bary | T-009, T-014 | Achieved
M-04 | Master and transactional data prepared | 2026-10-19 | Ahmed Mahmoud Mohamed | T-022 - T-027 | Achieved
M-05 | UAT documented and reviewed (simulated) | 2026-10-13 | Fathy Adel Fathy | T-029, T-030 | Achieved
M-06 | Final review and package validated | 2026-10-20 | Mohamed Mahmoud Abdel Bary | T-044, T-045 | Achieved

## Module Responsibility Matrix
Odoo Area | Responsible (does the work) | Configuration | File upload / data | Journals | Testing | Documentation | Reviewer
General settings, apps, companies and branches | Mohamed Mahmoud Abdel Bary | Install apps, company, branches, languages | Configure in Odoo; no data file | Not applicable | Settings review | Basic_Database_Configuration §1-5 | Mohamed Essam El-Din Youssef (review)
Users, access rights and approvals | Mohamed Mahmoud Abdel Bary | Groups, record rules, approval thresholds | Users created from placeholders | Not applicable | Access tests (SEC-001..005) | UPD_Users_Privileges | Omnia Haitham (review)
Sales and CRM | Mohamed Essam El-Din Youssef | Pricelists, quotation templates, pipeline stages, sales teams | Customers, pricelists, CRM sample (CSV 06, 16) | Sales journal INV used with Accounting | Sales and CRM test cases | BRD 6.2-6.3, UDP 3 | Mohamed Mahmoud Abdel Bary (review)
Purchase and vendors | Fathy Adel Fathy | RFQ/PO flow, approvals, vendor pricelists, quality checks | Vendors (CSV 07) | Vendor bills BILL journal with Accounting | Purchase and quality test cases | BRD 6.4, UDP 4 and 6 | Ahmed Mahmoud Mohamed (review)
Inventory and warehouses | Ahmed Mahmoud Mohamed | Warehouses, locations, routes, lots/serials, expiry, FEFO, reordering | Products, lots/serials, opening stock (CSV 02-05, 11-13) | Stock Journal STJ, valuation accounts with Accounting | Inventory test cases | BRD 6.5, SSD 6, UDP 5 | Fathy Adel Fathy (review)
Accounting and journals | Omnia Haitham | Chart, taxes, payment terms, fiscal settings, analytic plan | Chart, journals, mapping (CSV 08-10) | All journals: INV, BILL, STJ, MISC, OPEN, banks, cash safes | Accounting test cases and reconciliations | BRD 6.6, SSD 9, UDP 7 | Mohamed Mahmoud Abdel Bary (review)
Data upload (CSV import) | Ahmed Mahmoud Mohamed | Import order and dependencies, error handling | All CSV files (01-16) | Opening entry reviewed by Omnia Haitham | Counts, duplicates, keys | Import_Package README | Omnia Haitham (review)

## Summary
Project status summary (formulas)
Owner | Tasks | Completed | Avg Progress | Earliest Start | Latest End
Mohamed Mahmoud Abdel Bary | 13 | 13 | 100% | 2026-10-01 | 2026-10-20
Mohamed Essam El-Din Youssef | 12 | 12 | 100% | 2026-10-01 | 2026-10-18
Ahmed Mahmoud Mohamed | 10 | 10 | 100% | 2026-10-08 | 2026-10-20
Fathy Adel Fathy | 5 | 5 | 100% | 2026-10-08 | 2026-10-20
Omnia Haitham | 5 | 5 | 100% | 2026-10-11 | 2026-10-19
All tasks | 45 | 45 | 100% | 2026-10-01 | 2026-10-20
Tasks not at 100% | 0
Tasks without owner | 0
Overall completion | 100%
Formulas:
Earliest Start = MINIFS('Task List'!$F2:F46,'Task List'!$E2:E46,[Owner])
Earliest Start = MIN(E4:[Earliest Start, row above])
Latest End = MAXIFS('Task List'!$G2:G46,'Task List'!$E2:E46,[Owner])
Latest End = MAX(F4:[Latest End, row above])