REDLINE Medical Supplies & Equipment Trading ريد لاين للتجارة في المستلزمات والمعدات الطبية

Team Task Assignment

توزيع المهام على الفريق

Tasks, deliverables and dates for each of the five team members

| Project | Odoo ERP Implementation - Graduation Project (simulation) |
| --- | --- |
| Document code | RL-TTA-001 |
| Version | 1.0 (final) |
| Preparation date | 25 October 2026 |
| Business reporting period | 1 May 2026 – 30 September 2026 |
| Target platform | Odoo 19.0 (Enterprise edition assumed) |
| Prepared by | Mohamed Mahmoud Abdel Bary, Mohamed Essam El-Din Youssef, Ahmed Mahmoud Mohamed, Fathy Adel Fathy, Omnia Haitham |
| Currency | EGP - Egyptian Pound |

Disclaimer: all companies, partners, bank details and transactions in this project are fictional or illustrative simulation data. Nothing in this document claims that the configuration has been installed, imported or tested on a live Odoo server.

# 1. Team and roles

| ID | Name | Role | Tasks |
| --- | --- | --- | --- |
| TM-01 | Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | 13 |
| TM-02 | Mohamed Essam El-Din Youssef | Sales & CRM | 12 |
| TM-03 | Ahmed Mahmoud Mohamed | Inventory & Data Upload | 10 |
| TM-04 | Fathy Adel Fathy | Purchase, Quality & Testing | 5 |
| TM-05 | Omnia Haitham | Accounting & Finance | 5 |

Dates follow the dependency-driven task register (Project_Team_and_Roles.xlsx). All tasks are marked 100% at documentation level; nothing was installed or tested on a live Odoo server.

# 2. Mohamed Mahmoud Abdel Bary - Team Leader - Apps, Settings, Permissions & Design

| ID | Task | What to do | Deliverable | Start | End | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| T-001 | Project kick-off and charter | Define scope, objectives, governance, branch/warehouse structure and success criteria. | Project charter (in SSD §1) | 01 Oct | 01 Oct | Charter approved by the team leader |
| T-003 | Project team, roles and task register | Define five-member team, responsibilities, task register and milestones. | Project_Team_and_Roles.xlsx | 01 Oct | 01 Oct | Every deliverable has an accountable owner |
| T-004 | Odoo version and edition assumptions | Select version/edition, list standard vs Enterprise vs custom features. | Assumptions (BDC §1, TPD §2) | 01 Oct | 01 Oct | Version stated; unverified features flagged |
| T-009 | Gap analysis and workflow documentation (GAWF) | Compare manual baseline with proposed Odoo processes; propose solutions per gap. | GAWF_Gap_Analysis.docx | 07 Oct | 08 Oct | Each gap has solution, owner, priority, validation |
| T-011 | Solution architecture and module selection | Define modules, dependencies, single-company/multi-branch model, warehouse routes. | SSD §2-4 | 07 Oct | 08 Oct | Architecture approved |
| T-012 | Security model and approval workflows | Define roles, groups, record-rule limitations, approval thresholds and audit trail. | SSD §7 | 08 Oct | 11 Oct | Segregation of duties documented |
| T-013 | Process diagrams (P2P, O2C, receipt, transfers, returns, close) | Create workflow diagrams for six core processes. | SSD §8 | 08 Oct | 11 Oct | Diagrams consistent with requirements |
| T-014 | Solution Design Document (SSD) | Assemble SSD with reporting design and migration strategy. | SSD_Solution_Design.docx | 11 Oct | 12 Oct | SSD complete and reviewed |
| T-033 | Basic database configuration document | Document initial Odoo setup: company, users, groups, settings, taxes, backups. | Basic_Database_Configuration.docx | 12 Oct | 13 Oct | No real credentials included |
| T-037 | Users privileges document (UPD) | Define roles, groups, access matrix, approval limits and segregation of duties. | UPD_Users_Privileges.docx | 13 Oct | 14 Oct | Segregation of duties documented; no credentials |
| T-038 | Module configuration specifications (Sales/CRM, Purchase, Inventory, Accounting, general settings) | Specify app settings, journals, imports and access rights per Odoo area with the owner of each area. | Basic_Database_Configuration.docx §7-10; Runbook | 11 Oct | 12 Oct | Each Odoo area has an owner and a configuration checklist |
| T-042 | Presentation for graduation defense | Build 15-20 slide-style PDF. | PowerPoint_Presentation.pdf | 13 Oct | 14 Oct | Facts consistent with documents |
| T-044 | Final review and project coordination | Final governance sign-off and package approval. | Approval record | 20 Oct | 20 Oct | Approved by team leader |

# 3. Mohamed Essam El-Din Youssef - Sales & CRM

| ID | Task | What to do | Deliverable | Start | End | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| T-002 | Company profile and business context | Compile bilingual company profile, branches, warehouse network, product categories and customers. | Company_Profile.docx | 01 Oct | 04 Oct | Profile reviewed; facts consistent with the charter |
| T-005 | Stakeholder analysis and interviews (simulated) | Identify stakeholders, document as-is processes of the legacy/manual baseline. | BRD §3-4 | 04 Oct | 05 Oct | Stakeholder register approved |
| T-006 | As-is process documentation | Document manual quotation, purchasing, receiving, stock-card, invoicing and collection processes. | BRD §4; GAWF §3 | 05 Oct | 06 Oct | Processes validated with owners |
| T-007 | Functional and non-functional requirements | Write requirements with IDs, priorities, owners and acceptance criteria. | BRD §6-8 | 06 Oct | 07 Oct | All requirements baselined |
| T-008 | Business rules, roles and reporting requirements | Capture rules for credit, FEFO, quarantine, approvals; define reports and KPIs. | BRD §9-11 | 07 Oct | 08 Oct | Rules reviewed |
| T-010 | Requirements traceability matrix | Map each requirement to process, module, feature class, owner and test case. | RTM_Traceability_Matrix.xlsx | 07 Oct | 08 Oct | Every requirement linked to a test case |
| T-023 | Customer and vendor master data | Prepare 13 customers and 6 vendors (illustrative) with terms and credit limits. | Partners_and_Operations_Cycles.xlsx (sheets 1-2) | 11 Oct | 12 Oct | Partners flagged as illustrative |
| T-028 | Functional requirements validation | Validate requirements against design and data; resolve conflicts. | Validation notes (RTM) | 12 Oct | 13 Oct | No unresolved conflicts |
| T-034 | Business process and cycle documentation | Document the end-to-end cycles with examples from simulated records. | BRD §5; SSD §8 | 15 Oct | 18 Oct | Cycles tie to simulated data |
| T-035 | Project name and scope document | Define project identity, objectives, in/out of scope, deliverables, assumptions and acceptance criteria. | Project_Name_and_Scope.docx | 05 Oct | 06 Oct | Scope approved by the team leader |
| T-036 | CRM requirements and pipeline design | Define leads, opportunity stages, sales teams per branch, lost reasons and tender tracking; link won opportunities to sales orders. | BRD §6.3 (CRM); SSD CRM design; GAWF G-28, G-29 | 06 Oct | 07 Oct | CRM requirements CRM-001..CRM-008 baselined |
| T-039 | CRM pipeline sample data and CSV | Prepare simulated leads/opportunities linked to sales orders, stages and teams; add CSV 16 and reconciliation checks. | Partners_and_Operations_Cycles.xlsx (CRM Pipeline); Import_Package/16_crm_pipeline.csv | 15 Oct | 18 Oct | Won opportunities reconcile with non-retail sales orders |

# 4. Ahmed Mahmoud Mohamed - Inventory & Data Upload

| ID | Task | What to do | Deliverable | Start | End | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| T-015 | Technical proposal (TPD) | Define technical scope, integration, custom module proposals, testing, deployment, maintenance. | TPD_Technical_Proposal.docx | 08 Oct | 12 Oct | Custom work clearly labelled as proposed |
| T-017 | Organization, branches and warehouses setup design | Design branch representation and four-warehouse structure with locations and routes. | Organization_and_Accounting_Charts.xlsx (sheets 1-3) | 08 Oct | 11 Oct | Branches/warehouses consistent in all documents |
| T-020 | Product master, categories and tracking | Define 24 products with bilingual names, costs, tracking and expiry policies. | Products_and_Inventory_Data.xlsx (sheets 1-2) | 11 Oct | 12 Oct | Serial for equipment, lot+expiry for consumables |
| T-021 | Opening balances and reordering rules | Prepare warehouse opening stock and min/max rules. | Products_and_Inventory_Data.xlsx (sheets 3,8) | 12 Oct | 13 Oct | Opening value reconciles to opening journal |
| T-022 | Five-month stock movements, lots and serials | Generate coherent stock history with lot/serial registers and expiry tracking. | Products_and_Inventory_Data.xlsx (sheets 4-7,9-10) | 13 Oct | 14 Oct | Opening+in-out=closing for every product/warehouse |
| T-024 | Five-month sales and purchase cycles | Generate SOs, POs, deliveries, receipts, invoices, bills, payments and returns. | Partners_and_Operations_Cycles.xlsx (sheets 3-10) | 14 Oct | 15 Oct | Documents reconcile with stock and GL |
| T-026 | Data migration design and CSV import package | Define import order, dependencies, CSV files and README with limitations. | Import_Package/ (CSV + README) | 15 Oct | 18 Oct | Import order documented |
| T-027 | Data quality checks | Automated checks of keys, duplicates, dates and reconciliation. | Validation_Report | 18 Oct | 19 Oct | Zero structural errors |
| T-040 | Go-live and deployment plan | Define readiness criteria, cut-over, reconciliation, rollback and hypercare. | Go_Live_and_Deployment_Plan.docx | 18 Oct | 19 Oct | Cut-over and rollback steps documented |
| T-045 | ZIP packaging and validation report | Package deliverables and run automated validation. | RedLine_Odoo_Graduation_Project.zip; Validation_Report | 20 Oct | 20 Oct | All required files present and opening |

# 5. Fathy Adel Fathy - Purchase, Quality & Testing

| ID | Task | What to do | Deliverable | Start | End | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| T-029 | UAT scenario and test-case documentation | Write test cases covering the full lifecycle with simulated data references. | UATD_User_Acceptance_Testing.xlsx | 08 Oct | 12 Oct | Every requirement has a test case |
| T-030 | Simulated UAT review | Review expected behaviour of each test against the documented scenario; record status honestly. | UATD results (simulated) | 12 Oct | 13 Oct | Results labelled simulated; unverified items not marked passed |
| T-031 | User guides | Prepare role-based guides (sales, purchase, warehouse, quality, accounting). | UDP_Users_Guide.docx | 12 Oct | 14 Oct | Guides cover core tasks |
| T-032 | Training materials and plan | Prepare training outline, exercises and assessment tasks. | TD_Training_Document.docx | 14 Oct | 15 Oct | Plan approved |
| T-043 | Final quality assurance | Cross-document consistency check; fix defects. | Final QA notes | 19 Oct | 20 Oct | No inconsistencies |

# 6. Omnia Haitham - Accounting & Finance

| ID | Task | What to do | Deliverable | Start | End | Done when |
| --- | --- | --- | --- | --- | --- | --- |
| T-016 | Financial proposal (FPD) | Prepare illustrative EGP estimate with milestones, exclusions and VAT assumption. | FPD_Financial_Proposal.pdf | 12 Oct | 13 Oct | Totals verified arithmetically |
| T-018 | Chart of accounts and journals design | Design 101-account hierarchical chart, journals, bank/cash accounts. | Organization_and_Accounting_Charts.xlsx (sheets 4-5) | 11 Oct | 12 Oct | No duplicate codes; account types valid |
| T-019 | Accounting configuration, tax and account mapping | Define valuation, Anglo-Saxon, VAT 14% assumption and category-to-account mapping. | Organization_and_Accounting_Charts.xlsx (sheets 6-9) | 12 Oct | 13 Oct | Mapping reconciles with simulated journal entries |
| T-025 | Monthly summaries and transaction reconciliation | Summaries, receivable/payable roll-forward and ledger cross-checks. | Partners_and_Operations_Cycles.xlsx (sheets 11-12) | 15 Oct | 18 Oct | All checks pass or are explained |
| T-041 | Accounting procedures and month-end close checklist | Document accounting procedures, reconciliation steps and month-end close for Odoo. | Month-end close checklist (SSD / UDP section 7) | 18 Oct | 19 Oct | Checklist matches simulated reconciliations |