## README
RedLine Medical — User Acceptance Testing (UATD)
Project | RedLine Medical Supplies & Equipment Trading — Odoo ERP Graduation Project
Version / date | 1.0 — 2026-10-25
Target Odoo version | Odoo 19.0 (Enterprise edition assumed)
Business period used for test data | 1 May 2026 – 30 September 2026
IMPORTANT | No test was executed on a live Odoo server. 'Passed (simulated review)' means the expected behaviour was reviewed against the documented scenario and the simulated data (reconciliations in the three data workbooks). Tests depending on Enterprise/optional apps, proposed customizations, security or performance are 'Not Executed - requires live Odoo verification'.
Evidence | Evidence references are simulated cross-references to the data workbooks, not screenshots or logs from Odoo.
Execution / Review Date | Date the simulated review was recorded; blank when not executed.
Defects | No defects were logged because no live execution occurred. The Defect Log sheet is ready for use during real UAT.
Formulas | The Summary sheet counts results with COUNTIF/COUNTIFS.

## Test Cases
Test Case ID | Requirement ID | Module | Scenario | Preconditions | Test Data | Execution Steps | Expected Result | Recorded Result | Pass/Fail Status | Tester | Execution / Review Date | Evidence Reference | Defect ID
TC-001 | CON-001 | Contacts | Create a hospital customer with bilingual name and credit terms | User with Sales role; contact classification tags configured | CUS-001 Al Salam Teaching Hospital / مستشفى السلام التعليمي; terms 30 days; limit EGP 1,000,000 | 1. Contacts > New. 2. Enter English and Arabic names. 3. Set Payment Terms 30 Days and credit limit. 4. Save and open a new quotation for the customer. | Record saved; payment term and credit limit visible; customer selectable on quotation. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-001 (simulated data cross-reference) | None
TC-002 | CON-002 | Contacts | Create manufacturer vendor with payment terms | User with Purchase role | VEN-001 Helios Medical Systems GmbH (illustrative); terms 60 days; bank CIB | 1. Contacts > New. 2. Mark as vendor. 3. Set payment term 60 days. 4. Create an RFQ for the vendor. | Vendor saved; RFQ shows vendor and 60-day term. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-002 (simulated data cross-reference) | None
TC-003 | CON-003 | Contacts | Duplicate tax-ID warning | Tax ID uniqueness check enabled | Create partner with tax ID TAXID-PLACEHOLDER-001 twice | 1. Create partner with tax ID. 2. Create second partner with the same tax ID. | Second record raises duplicate warning or is blocked. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-004 | CON-004 | Contacts | Credit-limit breach on sales confirmation | Customer credit limit set; open receivables exist | CUS-002 limit EGP 2,000,000; confirm an order that pushes exposure above the limit | 1. Create a quotation above available credit. 2. Confirm. | Warning displayed on confirmation; hard block requires the proposed customization. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-005 | SAL-001 | Sales | Quotation with contract discount and 14% VAT | Pricelist with 3% discount for CUS-001 | Product EQ-MON-001 qty 2; list price EGP 54,500 | 1. Sales > New quotation for CUS-001. 2. Add product. 3. Check unit price, VAT and print PDF in Arabic. | Unit price = list price less 3%; VAT 14% added; PDF bilingual. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-005 (simulated data cross-reference) | None
TC-006 | SAL-002 | Sales | Quotation above EGP 500,000 requires approval | Approval rule configured | Quotation total EGP 1,250,000 for CUS-002 | 1. Create quotation above threshold. 2. Attempt to confirm as sales rep. 3. Approve as Sales Manager. | Confirmation blocked until approval is granted and logged. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-007 | SAL-003 | Sales | Order confirmation generates warehouse delivery | Stock available in EQP/CON | SO/2026/0001 (Al Salam Teaching Hospital) | 1. Confirm the sales order. 2. Open generated delivery orders. | One delivery per source warehouse is created with reserved stock. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-007 (simulated data cross-reference) | None
TC-008 | SAL-004 | Sales | Partial delivery and backorder | Order with insufficient delivered quantity | SO/2026/0076 — status: Partially Delivered (backorder open) | 1. Open delivery. 2. Set done quantity below demand. 3. Validate and create backorder. 4. Create invoice from delivered quantity. | Backorder created; invoice quantity equals delivered quantity (see Sales Order Lines: ordered > delivered). | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-008 (simulated data cross-reference) | None
TC-009 | SAL-005 | Sales | Sales analysis by branch | Analytic plan Branch applied | All invoices 1 May 2026 – 30 September 2026; compare branch totals with invoice total EGP 31,077,427 | 1. Open Sales Analysis. 2. Group by Branch. 3. Compare total to invoices. | Branch sub-totals add up to the invoiced net. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-010 | SAL-006 | Sales | Contract discount applied by pricelist | Pricelist assigned to CUS-009 (5%) | Product CN-GLV-001 qty 100 | 1. New quotation for CUS-009. 2. Add product. | Price equals list price less 5%. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-010 (simulated data cross-reference) | None
TC-011 | SAL-007 | Sales | Warranty end date for delivered serial | Warranty months set on product; serial delivered | Serial SN-AUT-2603-0001 delivered to CUS-011 on 2026-08-20; warranty end 2028-08-20 | 1. Open the serial in Traceability. 2. View warranty end date and status. | Warranty end date = delivery date + warranty months (requires proposed custom field/report). | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-012 | SAL-008 | Sales | Customer return received into quarantine and credited | Delivered and invoiced order | QRT/RET/0001 on INV/2026/00007: CN-SYR-001 qty 13, reason 'Damaged in transit'; credit note RINV/2026/00001 | 1. Open invoice > Reverse / Return. 2. Receive return in QRT/Quarantine. 3. Post credit note. | Stock enters QRT/Quarantine; credit note reverses revenue and VAT for the returned quantity. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-012 (simulated data cross-reference) | None
TC-013 | SAL-009 | Sales | Retail cash sale at Maadi | Retail customer CUS-013; Maadi cash safe journal CSH2 | SO/2026/0005 invoice INV/2026/00003 total EGP 3,990 | 1. Create order. 2. Deliver. 3. Invoice. 4. Register cash payment in CSH2. | Invoice paid in full on the same day; CSH2 increases. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-013 (simulated data cross-reference) | None
TC-014 | PUR-001 | Purchase | RFQ converted to PO | Vendor and products exist | PO/2026/0001 to Helios Medical Systems GmbH for warehouse EQP | 1. Create RFQ. 2. Confirm order. 3. Check receipt. | PO confirmed; receipt created for warehouse with expected date. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-014 (simulated data cross-reference) | None
TC-015 | PUR-002 | Purchase | PO above EGP 250,000 requires approval | Double validation threshold configured | MRI purchase PO/2026/0007 total EGP 18,500,000 | 1. Create PO above threshold. 2. Confirm as buyer. 3. Approve as manager. | State = To Approve until approved. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-015 (simulated data cross-reference) | None
TC-016 | PUR-003 | Purchase | Scheduler creates RFQs from reordering rules | Reordering rules defined; stock below minimum | First replenishment PO in period: PO/2026/0001 (2026-05-17) | 1. Inventory > Operations > Replenishment. 2. Run scheduler. 3. Review generated RFQs. | RFQs created per vendor up to max quantity. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-016 (simulated data cross-reference) | None
TC-017 | PUR-004 | Purchase | Bill matched to received quantity | Receipt validated | PO/2026/0004 received CON/IN/00001; bill BILL/2026/00001 | 1. Create bill from PO. 2. Compare billed qty with received qty. | Bill quantities equal received quantities; net EGP 102,828. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-017 (simulated data cross-reference) | None
TC-018 | PUR-005 | Purchase | Supplier return of failed-inspection goods | Failed QC; stock in QRT | QRT/SRET/0001: EQ-SUR-001 lot SN-SUR-2606-0017 qty 1 to Pharos Surgical Supplies | 1. Create return from the bill's receipt. 2. Validate from QRT to vendor. 3. Post debit note. | Payable reduced by debit note; stock leaves QRT. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-018 (simulated data cross-reference) | None
TC-019 | PUR-006 | Purchase | Serial-tracked equipment purchase (MRI) | Capital equipment product tracked by serial | PO/2026/0007: EQ-MRI-001 qty 1 from VEN-002 | 1. Create manual PO. 2. Receive and enter serial number. 3. Confirm quantity 1. | Serial created and linked to receipt; on-hand = 1 in EQP. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-019 (simulated data cross-reference) | None
TC-020 | PUR-007 | Purchase | Consumables purchase with lot and expiry | Product CN-GLV-001 lot + expiry tracked | Receipt of CN-GLV-001 with vendor lot and expiry | 1. Validate receipt. 2. Enter lot and expiry date for each line. | Validation requires lot and expiry; lot appears in Lot register. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Fathy Adel Fathy | 2026-10-13 | SIM-EVD-020 (simulated data cross-reference) | None
TC-021 | INV-001 | Inventory | Two-step receipt and putaway | Warehouse CON set to 2-step reception | A receipt for CON | 1. Validate receipt into CON/Input. 2. Process internal putaway to CON/Stock. | Stock available only after putaway. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-021 (simulated data cross-reference) | None
TC-022 | INV-002 | Inventory | Failed incoming inspection routed to quarantine | Quality control point on receipts | A receipt line fails QC (see Customer and Supplier Returns: SRET) | 1. Open quality check. 2. Mark Fail. 3. Create transfer to QRT. | Failed units are moved to QRT/Quarantine and blocked from sale (Quality app = Enterprise). | Not run. Behaviour depends on enterprise feature / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-023 | INV-003 | Inventory | Lot assignment on receipt | Lot-tracked product | Lot register in Products workbook | 1. Receive lot-tracked product. 2. Assign lot names. | Lot quantities match the register. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-023 (simulated data cross-reference) | None
TC-024 | INV-004 | Inventory | Serial numbers on receipt | Serial-tracked product | Serial register entries for EQ-INF-001 | 1. Receive 4 units. 2. Generate/import serials. | Four unique serials; duplicates rejected. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-024 (simulated data cross-reference) | None
TC-025 | INV-005 | Inventory | Expiry date shown on lots | Expiration dates enabled | Lot register (expiry column) | 1. Open a lot. 2. Verify expiry, alert and removal dates. | Dates match the Lot and Batch Register. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-025 (simulated data cross-reference) | None
TC-026 | INV-006 | Inventory | FEFO picks earliest-expiry lot first | Removal strategy FEFO on category MED-CON | CON/OUT/00010: CN-MSK-001 picked LOT-MSK-2602A1 x171 (exp 2027-03-12); LOT-MSK-2603B2 x326 (exp 2027-08-26) | 1. Reserve the delivery. 2. Compare reserved lots with expiry dates. | Lots reserved in ascending expiry order. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-026 (simulated data cross-reference) | None
TC-027 | INV-007 | Inventory | Near-expiry alert and report | Alert time = 60 days | Lot LOT-PAD-2602A1 (CN-PAD-001) expires 2026-11-25 with 20 units in QRT | 1. Run Near-Expiry report. 2. Filter Days to Expiry <= 60. | Flagged lot appears; sale of lots with <60 days is excluded by process. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-028 | INV-008 | Inventory | Inter-warehouse transfer without double counting | Two internal warehouses | INT/00002: SP-BAT-001 qty 6 SPR → EQP on 2026-06-15 | 1. Create internal transfer. 2. Validate. | Source decreases, destination increases; company total unchanged. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-028 (simulated data cross-reference) | None
TC-029 | INV-009 | Inventory | Quarantine transfer for damaged stock | QRT warehouse configured as non-sellable | SCRAP/0001: CN-SYR-001 lot LOT-SYR-2603A1 | 1. Transfer item to QRT. 2. Try to reserve it on a delivery. | Item not reservable. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-029 (simulated data cross-reference) | None
TC-030 | INV-010 | Inventory | Scrap expired lot to expiry-loss account | Scrap reason Expired mapped to 540200 | SCRAP/0003 on 2026-06-30 value EGP 46,000 | 1. Create scrap order. 2. Validate. 3. Open journal entry. | Dr 540200 / Cr inventory 130200 at cost. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-031 | INV-011 | Inventory | Cycle-count shortage adjustment | Inventory adjustment enabled | ADJ/2026/0002: Physical count shortage (cycle count) | 1. Inventory > Adjustments. 2. Apply counted quantity. 3. Review entry. | On-hand updated; Dr 540100 / Cr inventory. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-031 (simulated data cross-reference) | None
TC-032 | INV-012 | Inventory | Reordering rules loaded | Rules imported | Reordering Rules sheet (24 products; 23 with rules) | 1. Open Reordering Rules. 2. Compare with the sheet. | Rules equal Min/Max/Multiple per product. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-032 (simulated data cross-reference) | None
TC-033 | INV-013 | Inventory | Recall trace for a lot / serial | Traceability report enabled | Serial SN-AUT-2603-0001 → customer CUS-011 | 1. Inventory > Traceability. 2. Enter serial. 3. View upstream and downstream. | Report lists vendor receipt and customer delivery. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-033 (simulated data cross-reference) | None
TC-034 | INV-014 | Inventory | Pick then ship | 2-step delivery on EQP | Delivery from EQP | 1. Validate pick. 2. Validate ship. | Stock leaves EQP/Output on ship. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-034 (simulated data cross-reference) | None
TC-035 | INV-015 | Inventory | Negative stock blocked | Negative quantities disallowed | Deliver 99,999 units of CN-GLV-001 | 1. Reserve. 2. Force validation. | Validation refused; no negative stock. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-035 (simulated data cross-reference) | None
TC-036 | INV-016 | Inventory | Barcode scan selects product | Barcode app installed | Barcode 6229990000034 | 1. Open Barcode app. 2. Scan. | Product selected. | Not run. Behaviour depends on optional app / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-037 | INV-017 | Inventory | Valuation report equals GL | Automated valuation | Inventory total EGP 24,536,323 at 30-Sep-2026 | 1. Open valuation report. 2. Compare to accounts 1301xx-1303xx. | Totals equal. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-037 (simulated data cross-reference) | None
TC-038 | ACC-001 | Accounting | Invoice posting with VAT and branch | Delivered order | INV/2026/00001: net EGP 134,007, VAT EGP 18,761 | 1. Create invoice from order. 2. Post. 3. Review journal entry. | Dr 120100 total; Cr revenue and 220100; branch analytic. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-038 (simulated data cross-reference) | None
TC-039 | ACC-002 | Accounting | Vendor bill posting | Receipt validated | BILL/2026/00001 net EGP 102,828 VAT EGP 14,395 | 1. Create bill. 2. Post. | Dr 210500 and 140300; Cr 210100. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-039 (simulated data cross-reference) | None
TC-040 | ACC-003 | Accounting | Partial payment keeps invoice open | Invoice posted | INV/2026/00015 total EGP 64,350, paid EGP 38,610 in 1 receipts | 1. Register payment of part of the amount. 2. Register second payment. | Invoice shows partial then paid. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-040 (simulated data cross-reference) | None
TC-041 | ACC-004 | Accounting | Credit note reduces receivable | Posted invoice | RINV/2026/00001 against INV/2026/00007 EGP 2,889 | 1. Add credit note. 2. Post. | Dr 420100 and 220100; Cr 120100. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-041 (simulated data cross-reference) | None
TC-042 | ACC-005 | Accounting | COGS recognised at FIFO cost | Automated valuation | Delivery and invoice of INV/2026/00001 | 1. Validate delivery. 2. Post invoice. 3. Review entries. | Dr COGS / Cr 130600 at cost; margin matches product cost. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-042 (simulated data cross-reference) | None
TC-043 | ACC-006 | Accounting | VAT 14% totals | Taxes configured | Output VAT EGP 4,232,652 / input VAT EGP 3,436,752 | 1. Run VAT report. 2. Compare accounts. | Equal. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-044 | ACC-007 | Accounting | Branch P&L | Analytic plan applied | P&L filtered by BR-NSC / BR-MAA / BR-MOH | 1. Open P&L. 2. Group by Branch. | Branches add up to total. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-045 | ACC-008 | Accounting | Lock date prevents back-posting | Lock date 2026-09-30 | Post an entry dated 2026-09-15 | 1. Create journal entry. 2. Post. | Posting blocked for non-advisers. | Not run. Behaviour depends on standard / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-046 | ACC-009 | Accounting | Aged receivables total | Invoices open | Receivables EGP 29,532,073 at 30-Sep-2026 | 1. Open Aged Receivable. 2. Compare total. | Total equals 120100. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-046 (simulated data cross-reference) | None
TC-047 | ACC-010 | Accounting | Chart of accounts import | CSV prepared | 101 accounts (Organization_and_Accounting_Charts.xlsx) | 1. Import CSV. 2. Check for errors and types. | 101 accounts, no duplicates. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-047 (simulated data cross-reference) | None
TC-048 | ACC-011 | Accounting | Bank statement reconciliation | CIB journal | CIB statement lines for September | 1. Import statement. 2. Reconcile. | Suspense zero. | Not run. Behaviour depends on enterprise feature / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-049 | ACC-012 | Accounting | Stock-to-GL reconciliation | Month-end | Valuation EGP 24,536,323 | 1. Compare valuation to accounts 130100-130300. | Difference zero. | Not run. Behaviour depends on manual procedure / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-050 | RPT-001 | Reporting | Sales analysis equals invoices | Posted documents | Net sales after returns EGP 30,233,232 | 1. Open sales analysis. | Totals equal. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-050 (simulated data cross-reference) | None
TC-051 | RPT-002 | Reporting | KPI dashboard | Dashboard configured | KPIs in BRD | 1. Open dashboard. | KPIs visible. | Not run. Behaviour depends on enterprise feature / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Omnia Haitham (planned) |  | None (no live execution) | None
TC-052 | CRM-001 | CRM | Lead capture and qualification | Sales team configured | OPP lead from source 'Hospital tender' | 1. Create lead. 2. Qualify and convert to opportunity. | Opportunity created with source retained. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-052 (simulated data cross-reference) | None
TC-053 | CRM-002 | CRM | Pipeline stages and probability | Stages configured | OPP-0062: stage New | 1. Open pipeline board. 2. Move card to next stage. | Probability updates with stage; expected revenue totals per stage. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-053 (simulated data cross-reference) | None
TC-054 | CRM-003 | CRM | Quotation from opportunity marks Won | Opportunity exists | OPP-0001 linked to SO/2026/0001 | 1. Create quotation from opportunity. 2. Confirm order. | Opportunity moves to Won and links the sales order. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-054 (simulated data cross-reference) | None
TC-055 | CRM-004 | CRM | Sales teams per branch | Teams defined | Teams: Nasr City, Maadi, Mohandeseen | 1. Open pipeline analysis. 2. Group by sales team. | Opportunities and revenue grouped per branch team. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-055 (simulated data cross-reference) | None
TC-056 | CRM-005 | CRM | Activities and reminders | Opportunity exists | Call scheduled for OPP-0062 | 1. Schedule call. 2. Let due date pass. | Overdue activity highlighted. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-056 (simulated data cross-reference) | None
TC-057 | CRM-006 | CRM | Pipeline forecast and win rate | Opportunities in several stages | Won 62, lost 14, open 10 | 1. Open forecast report. 2. Group by month. | Expected and weighted revenue shown; win rate computed. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-057 (simulated data cross-reference) | None
TC-058 | CRM-007 | CRM | Lost reason required | Opportunity open | OPP-0016: reason Competitor selected | 1. Mark opportunity Lost. | Lost reason is mandatory and appears in lost analysis. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-058 (simulated data cross-reference) | None
TC-059 | CRM-008 | CRM | Tender tracking fields | Custom fields (proposed) | Tender reference and deadline | 1. Add fields/tags. 2. Filter by deadline. | Tender opportunities filterable by deadline. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Essam El-Din Youssef (planned) |  | None (no live execution) | None
TC-060 | RPT-003 | Reporting | Margin by category | COGS posted | Monthly Business Summary | 1. Open margin report. | Matches summary. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-060 (simulated data cross-reference) | None
TC-061 | RPT-004 | Reporting | Customer statement | Open invoices | CUS-003 statement | 1. Print statement. | Open invoices listed. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Omnia Haitham | 2026-10-13 | SIM-EVD-061 (simulated data cross-reference) | None
TC-062 | SEC-001 | Security | Role access | Groups defined | Sales rep tries Accounting | 1. Login as sales rep. | Menu hidden. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Mahmoud Abdel Bary (planned) |  | None (no live execution) | None
TC-063 | SEC-002 | Security | Branch-restricted visibility | Record rules | Maadi user | 1. Login as Maadi user. | Only Maadi records. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Mahmoud Abdel Bary (planned) |  | None (no live execution) | None
TC-064 | SEC-003 | Security | Audit trail on price change | Tracking on | Change credit limit | 1. Edit limit. | Chatter shows change. | Not run. Behaviour depends on standard / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Mahmoud Abdel Bary (planned) |  | None (no live execution) | None
TC-065 | SEC-004 | Security | Segregation of duties | Rules defined | Approve own PO | 1. Create PO. 2. Approve own PO. | Rejected. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Mahmoud Abdel Bary (planned) |  | None (no live execution) | None
TC-066 | SEC-005 | Security | Backup and restore | Backup job | Restore to test DB | 1. Run backup. 2. Restore. | Counts match. | Not run. Behaviour depends on manual procedure / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Mohamed Mahmoud Abdel Bary (planned) |  | None (no live execution) | None
TC-067 | NFR-001 | Non-functional | Arabic RTL print | Arabic installed | Invoice printed in Arabic | 1. Switch language. 2. Print. | RTL layout. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Fathy Adel Fathy (planned) |  | None (no live execution) | None
TC-068 | NFR-002 | Non-functional | Cairo timezone and EGP format | Settings applied | Create document at 23:30 | 1. Create document. | Cairo time; EGP 2 decimals. | Not run. Behaviour depends on standard (configuration) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Fathy Adel Fathy (planned) |  | None (no live execution) | None
TC-069 | NFR-003 | Non-functional | Screen response time | Test server | 1,000-line list | 1. Open list. | < 3 s. | Not run. Behaviour depends on manual procedure / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Fathy Adel Fathy (planned) |  | None (no live execution) | None
TC-070 | NFR-004 | Non-functional | User training task completion | Training delivered | Role scripts | 1. Run scripts. | Tasks completed. | Not run. Behaviour depends on manual procedure / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Fathy Adel Fathy (planned) |  | None (no live execution) | None
TC-071 | MIG-001 | Migration | Import chart and journals | CSV | coa.csv, journals.csv | 1. Import. | Counts equal. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-071 (simulated data cross-reference) | None
TC-072 | MIG-002 | Migration | Import products | CSV | 24 products | 1. Import. | 24 products with tracking flags. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-072 (simulated data cross-reference) | None
TC-073 | MIG-003 | Migration | Import partners | CSV | 13 customers, 6 vendors | 1. Import. | Counts equal. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-073 (simulated data cross-reference) | None
TC-074 | MIG-004 | Migration | Opening stock load | Lots exist | Opening value EGP 24,170,200 | 1. Import adjustment. | Value equals. | Not run. Behaviour depends on standard / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-075 | MIG-005 | Migration | History load limitation | — | Five-month history | 1. Review approach. | Documented limitation. | Not run. Behaviour depends on customization (proposed) / further technical verification; planned for the pilot environment. | Not Executed - requires live Odoo verification | Ahmed Mahmoud Mohamed (planned) |  | None (no live execution) | None
TC-076 | SAL-008 | Sales | Restock after inspection | Return received | QRT/RET/0007: CN-TUB-001 (Excess quantity / order change) restocked after inspection | 1. Inspect. 2. Transfer QRT→home warehouse. | Stock returns to sellable location. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Mohamed Essam El-Din Youssef | 2026-10-13 | SIM-EVD-076 (simulated data cross-reference) | None
TC-077 | INV-011 | Inventory | Cycle-count gain adjustment | Count approved | ADJ/2026/0001: Physical count gain (cycle count) | 1. Apply count. 2. Review entry. | Dr inventory / Cr 540100. | Expected behaviour reviewed against the documented scenario and the simulated data; no live Odoo execution. | Passed (simulated review) | Ahmed Mahmoud Mohamed | 2026-10-13 | SIM-EVD-077 (simulated data cross-reference) | None

## Summary
UAT summary (formulas)
Total test cases | 77
Passed (simulated review) | 50
Failed | 0
Not executed - requires live Odoo verification | 27
Passed on live Odoo | 0
Distinct requirements covered | 75
By module
Module | Tests | Passed (simulated) | Not executed
Contacts | 4 | 2 | 2
Sales | 10 | 7 | 3
CRM | 8 | 7 | 1
Purchase | 7 | 7 | 0
Inventory | 18 | 14 | 4
Accounting | 12 | 7 | 5
Reporting | 4 | 3 | 1
Security | 5 | 0 | 5
Non-functional | 4 | 0 | 4
Migration | 5 | 3 | 2
Total | 77 | 50 | 27

## Defect Log
Defect ID | Test Case ID | Description | Severity | Status | Reported By | Reported Date | Resolution
(none) |  | No defects recorded - no live Odoo execution has taken place.