REDLINE Medical Supplies & Equipment Trading ريد لاين للتجارة في المستلزمات والمعدات الطبية

Go-Live and Deployment Plan

خطة التشغيل الفعلي والنشر

Cut-over, deployment, validation, rollback, hypercare and ownership

| Project | Odoo ERP Implementation - Graduation Project (simulation) |
| --- | --- |
| Document code | RL-GLP-001 |
| Version | 1.0 (final) |
| Preparation date | 25 October 2026 |
| Business reporting period | 1 May 2026 – 30 September 2026 |
| Target platform | Odoo 19.0 (Enterprise edition assumed) |
| Prepared by | Mohamed Mahmoud Abdel Bary, Mohamed Essam El-Din Youssef, Ahmed Mahmoud Mohamed, Fathy Adel Fathy, Omnia Haitham |
| Currency | EGP - Egyptian Pound |

Disclaimer: all companies, partners, bank details and transactions in this project are fictional or illustrative simulation data. Nothing in this document claims that the configuration has been installed, imported or tested on a live Odoo server.

# Contents

| 1 | Objectives and approach |
| --- | --- |
| 2 | Readiness criteria |
| 3 | Environments and deployment steps |
| 4 | Cut-over plan |
| 5 | Data load and reconciliation |
| 6 | Go / No-Go decision |
| 7 | Rollback plan |
| 8 | Hypercare and support |
| 9 | Roles and responsibilities |
| 10 | Risks |
| 11 | Timeline (proposed) |

Section numbers are used for cross-references throughout the document set (e.g. 'SSD 4.2' = Solution Design Document, section 4.2).

# 1. Objectives and approach

Move RedLine from the manual process to Odoo 19.0 (Enterprise edition assumed) with minimal disruption: configure and rehearse on staging, migrate master data and opening balances, run a controlled cut-over, then provide hypercare. This is a plan only; no live deployment has been performed.

# 2. Readiness criteria

| Area | Criterion | Owner | Evidence |
| --- | --- | --- | --- |
| Configuration | Settings per BDC applied on staging | Mohamed Mahmoud Abdel Bary | Configuration checklist |
| Data | Import package loaded twice with no errors; reconciliations pass | Ahmed Mahmoud Mohamed | Import log, reconciliation sheet |
| UAT | All Must requirements pass on live staging; no open critical defects | Fathy Adel Fathy | UATD results |
| Training | All mandatory sessions attended; assessments passed | Fathy Adel Fathy | Attendance and results |
| Accounting | Chart, VAT and opening balances approved by accountant | Omnia Haitham / Finance Manager | Sign-off |
| Infrastructure | Backups and restore tested; production access ready | Ahmed Mahmoud Mohamed | Restore test record |
| Business | Sponsor sign-off | General Manager | Go-live approval form |

# 3. Environments and deployment steps

| Step | Activity | Owner |
| --- | --- | --- |
| 1 | Provision production database (hosting option decided: Odoo Online / Odoo.sh / on-premise) | Ahmed Mahmoud Mohamed |
| 2 | Install apps and configure settings; set company, branches, warehouses, taxes, journals | Mohamed Mahmoud Abdel Bary |
| 3 | Install proposed custom module (if approved) after staging tests | Ahmed Mahmoud Mohamed |
| 4 | Create users and groups per UPD; enable MFA for administrators | Ahmed Mahmoud Mohamed |
| 5 | Apply report templates (Arabic/RTL), print layouts, email server | Ahmed Mahmoud Mohamed |
| 6 | Configure scheduled backups and monitoring | Ahmed Mahmoud Mohamed |

# 4. Cut-over plan

Cut-over is scheduled on a Friday/Saturday weekend to avoid business hours. Legacy records are frozen at the agreed time.

| When | Activity | Owner |
| --- | --- | --- |
| T-7 days | Final rehearsal on staging; freeze configuration | Team |
| T-2 days | Communicate cut-over to staff, customers and vendors | General Manager |
| T-1 day (Thursday) | Complete open deliveries/receipts; month-to-date reconciliations in legacy | Warehouse / Accounting |
| Friday | Final physical count; export stock by lot/serial; export open invoices and bills | Warehouse / Accounting |
| Friday | Import: accounts, journals, warehouses, categories, partners, products, lots/serials | Ahmed Mahmoud Mohamed |
| Saturday | Opening stock by location/lot, opening receivables and payables; reconciliation | Ahmed Mahmoud Mohamed, Finance |
| Saturday | Smoke test of key flows (sale, purchase, transfer, return) | Fathy Adel Fathy |
| Saturday evening | Go / No-Go decision | General Manager |
| Sunday | Go-live; hypercare starts | Team |

# 5. Data load and reconciliation

| Item | Expected (simulation baseline) | Check |
| --- | --- | --- |
| Accounts | 101 | Count and unique codes |
| Products | 24 | Count; tracking flags |
| Customers / vendors | 13 / 6 | Count; terms; credit limits |
| Serials | 186 | Distinct count; warranty fields |
| CRM opportunities (sample) | 86 (won 62 / lost 14 / open 10) | Won link to sales orders; stages and teams created first |
| Lots | 42 rows | Expiry dates; none < 60 days in sellable stock |
| Opening inventory value | EGP 24,170,200.00 (simulation) | Valuation vs opening journal |
| Receivables / payables | Per legacy at cut-over date | Control accounts vs partner ledgers |
| Trial balance | Balanced | Debits = credits |

The figures above come from the simulated dataset; real values will replace them at cut-over.

# 6. Go / No-Go decision

| Criterion | Go if |
| --- | --- |
| Data reconciliation | All checks pass or differences explained and approved |
| Smoke tests | No critical failures |
| Users | Accounts active; super-users available |
| Backup | Pre-go-live backup completed and verified |
| Sponsor | General Manager approves |

# 7. Rollback plan

Trigger: critical data error or blocking defect found before Sunday opening that cannot be fixed within the cut-over window.

Action: restore pre-load backup; continue on the legacy process; reschedule the cut-over after correction.

After go-live: no rollback of posted transactions; corrections are made by reversing entries and adjustments.

Legacy files remain read-only for 30 days.

# 8. Hypercare and support

| Period | Support |
| --- | --- |
| Weeks 1-2 | Daily stand-up; on-site/remote support; issue log with severity |
| Weeks 3-4 | Review twice weekly; fixes batched |
| After first month-end | Close review; refresher training; formal handover |

| Severity | Definition | Target response |
| --- | --- | --- |
| Critical | Cannot sell, deliver, invoice or post | 1 hour |
| High | Workaround exists but heavy impact | 4 hours |
| Medium | Minor impact | 2 working days |
| Low | Cosmetic / request | Backlog |

# 9. Roles and responsibilities

| Name | Role | Go-live responsibility |
| --- | --- | --- |
| Mohamed Mahmoud Abdel Bary | Team Leader - Apps, Settings, Permissions & Design | App installation, general settings, companies and branches; Go-live support for this area |
| Mohamed Essam El-Din Youssef | Sales & CRM | Sales and CRM configuration: pipeline, quotations, pricelists, sales teams; Go-live support for this area |
| Ahmed Mahmoud Mohamed | Inventory & Data Upload | Inventory configuration: warehouses, locations, routes, lots, serials, expiry, FEFO; Go-live support for this area |
| Fathy Adel Fathy | Purchase, Quality & Testing | Purchase configuration: vendors, RFQ and PO, approvals, vendor pricelists; Go-live support for this area |
| Omnia Haitham | Accounting & Finance | Accounting configuration: chart of accounts, journals, taxes, payment terms; Go-live support for this area |

# 10. Risks

| Risk | Mitigation |
| --- | --- |
| Data errors in lots/serials | Two rehearsals; automated validation |
| Staff unfamiliarity | Training; super-users; hypercare |
| Edition lacks a required feature | Verify early; fallback manual checklist |
| Tax/accounting misconfiguration | Accountant sign-off before go-live |
| Business interruption | Weekend cut-over; legacy read-only fallback |

# 11. Timeline (proposed)

| Phase | Duration | Outcome |
| --- | --- | --- |
| Staging build and live UAT | 3 weeks | Open UAT cases closed |
| Training | 1 week | Competency sign-off |
| Rehearsals | 1 week | Two successful data loads |
| Cut-over weekend | 2 days | Go-live |
| Hypercare | 4 weeks | Stable operations; handover |